## Sheet1
Data Date | 2026-02-04
Project Name | AZTAC Lmited
Layout Name | 30d lookahead
Weekend | Saturday, Sunday
Level 1 | Task ID | Task Name | Task Type | Start | Finish | % Completed | Predecessor | Predecessor Details
Substructure | A101 | Start | Start Milestone | 2026-02-01 |  | 100%
Substructure | A102 | Excavation | Task Dependent | 2026-02-02 | 2026-02-03 | 100% | A101 | A101: FS
Substructure | A103 | PCC | Task Dependent | 2026-02-03 | 2026-02-07 | 25% | A102 | A102: FS
Substructure | A104 | Curing | Task Dependent | 2026-02-04 | 2026-02-10 | 2% | A103 | A103: FS
Superstructure | A105 | Side Shutter | Task Dependent | 2026-02-05 | 2026-02-09 | 0% | A104 | A104: FS
Superstructure | A106 | Rebar | Task Dependent | 2026-02-06 | 2026-02-12 | 0% | A105 | A105: FS
Superstructure | A107 | Concrete | Task Dependent | 2026-02-13 | 2026-02-15 | 0% | A106 | A106: FS
Superstructure | A108 | Task 1 | Task Dependent | 2026-02-16 | 2026-02-22 | 0% | A107 | A107: FS
Finishes | A109 | Task 2 | Task Dependent | 2026-02-23 | 2026-03-01 | 0% | A108 | A108: FS
Finishes | A110 | Task 3 | Task Dependent | 2026-03-02 | 2026-03-08 | 0% | A109 | A109: FS
Finishes | A111 | Task 4 | Task Dependent | 2026-03-09 | 2026-03-15 | 0% | A110 | A110: FS
Finishes | A112 | Task 5 | Task Dependent | 2026-03-16 | 2026-03-22 | 0% | A111 | A111: FS
Finishes | A113 | Task 6 | Task Dependent | 2026-03-23 | 2026-03-29 | 0% | A112 | A112: FS
Finishes | A114 | Task 7 | Task Dependent | 2026-03-30 | 2026-04-05 | 0% | A113 | A113: FS
Finishes | A115 | Task 8 | Task Dependent | 2026-04-06 | 2026-04-12 | 0% | A114 | A114: FS
Finishes | A1145 | Task 90 | Finish Milestone |  | 2028-01-22 | 0% | A115 | A114: FF
Finishes | A2900 | Task 80 | Finish Milestone |  | 2028-01-12 | 0%
Finishes | A116 | Task 9 | Task Dependent | 2026-04-13 | 2026-04-19 | 0% | A115 | A115: FS
Section 04 | A117 | Task 10 | Task Dependent | 2026-04-20 | 2026-05-20 | 0% | A116 | A116: FS
Section 04 | A118 | Task 11 | Task Dependent | 2026-05-21 | 2026-06-20 | 0% | A117 | A117: FS
Section 04 | A119 | Task 12 | Task Dependent | 2026-06-21 | 2026-07-21 | 0% | A118 | A118: FS
Section 04 | A120 | Task 13 | Task Dependent | 2026-07-22 | 2026-08-21 | 0% | A119 | A119: FS
Section 04 | A121 | Task 14 | Task Dependent | 2026-08-22 | 2026-09-21 | 0% | A120 | A120: FS
Section 04 | A122 | Task 15 | Task Dependent | 2026-09-22 | 2026-10-22 | 0% | A121 | A121: FS
Section 04 | A123 | Task 16 | Task Dependent | 2026-10-23 | 2026-11-22 | 0% | A122 | A122: FS
Section 04 | A124 | Task 17 | Task Dependent | 2026-11-23 | 2026-12-23 | 0% | A123 | A123: FS
Section 04 | A125 | Task 18 | Task Dependent | 2026-12-24 | 2027-01-23 | 0% | A124 | A124: FS
Section 04 | A126 | Task 19 | Task Dependent | 2027-01-24 | 2027-02-23 | 0% | A125 | A125: FS
Section 05 | A127 | Task 20 | Task Dependent | 2027-02-24 | 2027-03-26 | 0% | A126 | A126: FS
Section 05 | A128 | Task 21 | Task Dependent | 2027-03-27 | 2027-04-26 | 0% | A127 | A127: FS
Section 05 | A129 | Task 22 | Task Dependent | 2027-04-27 | 2027-05-27 | 0% | A128 | A128: FS
Section 05 | A130 | Task 23 | Task Dependent | 2027-05-28 | 2027-06-27 | 0% | A129 | A129: FS
Section 05 | A131 | Task 24 | Task Dependent | 2027-06-28 | 2027-07-28 | 0% | A130 | A130: FS
Section 05 | A132 | Task 25 | Task Dependent | 2027-07-29 | 2027-08-28 | 0% | A131 | A131: FS
Section 05 | A133 | Task 26 | Task Dependent | 2027-08-29 | 2027-09-28 | 0% | A132 | A132: FS
Section 05 | A134 | Task 27 | Task Dependent | 2027-08-29 | 2027-09-28 | 0% | A133 | A133: SS
Section 05 | A135 | Task 28 | Task Dependent | 2027-09-29 | 2027-10-29 | 0% | A134, A1145, A1145 | A134: FS, A1145: FS, A1145: FF
Section 05 | A136 | Task 29 | Task Dependent | 2027-10-30 | 2027-11-29 | 0% | A135 | A135: FS
Section 05 | A137 | Task 30 | Task Dependent | 2027-11-30 | 2027-12-30 | 0% | A136 | A136: FS
Section 05 | A138 | Task 31 | Task Dependent | 2027-12-31 | 2028-01-30 | 0% | A137 | A137: FS
Section 06 | A139 | Task 32 | Task Dependent | 2028-01-31 | 2028-03-01 | 0% | A138, A2900 | A138: FS, A2900: FS
Section 06 | A140 | Task 33 | Task Dependent | 2028-03-02 | 2028-04-01 | 0% | A139 | A139: FS
Section 06 | A141 | Task 34 | Task Dependent | 2028-04-02 | 2028-05-02 | 0% | A140 | A140: FS
Section 06 | A142 | Task 35 | Task Dependent | 2028-05-03 | 2028-06-02 | 0% | A141 | A141: FS
Section 06 | A143 | Task 36 | Task Dependent | 2028-06-03 | 2028-07-03 | 0% | A142 | A142: FS
Section 06 | A144 | Task 37 | Task Dependent | 2028-07-04 | 2028-08-03 | 0% | A143 | A143: FS
Section 06 | A145 | Task 38 | Task Dependent | 2028-08-04 | 2028-09-03 | 0% | A144 | A144: FS
Section 06 | A146 | Finish | Finish Milestone |  | 2028-09-03 | 0% | A145 | A145:FF
Formulas:
Start = [Start, row above]+1
Start = [Finish, row above]+1
Finish = [Start]+1
Finish = [Finish, row above]