## Sheet1
Data Date | 2026-05-25
Project Name | Carbody
Layout Name | High Level View
Weekend | Saturday, Sunday
Level 1 | Task ID | Task Name | Task Type | Start | Finish | % Completed | Predecessor | Predecessor Details
Phase 0 | A102 | Engineering Package 01 Confirm | Finish Milestone |  | 2025-09-23 | 100%
Phase 0 | A103 | Engineering Package 02 Confirm | Finish Milestone |  | 2025-10-09 | 100%
Phase 0 | A104 | Engineering Package 03 Confirm | Finish Milestone |  | 2025-12-02 | 100%
Phase 0 | A110 | Engineering Package 04 Confirm | Finish Milestone |  | 2026-06-09 | 0%
Phase 0 | A105 | Engineering Package 05 Confirm | Finish Milestone |  | 2025-08-16 | 100%
Phase 0 | A106 | Engineering Package 06 Confirm | Finish Milestone |  | 2025-12-17 | 100%
Phase 01 | A107 | Production - Carbody | Task Dependent | 2026-03-26 | 2026-06-29 | 65% | A102, A105 | A102: FS, A105: FS
Phase 01 | A108 | Production - Fitouts | Task Dependent | 2026-03-26 | 2026-06-29 | 65% | A103, A105 | A103: FS, A105: FS
Phase 02 | A109 | Testing - Carbody | Task Dependent | 2026-03-26 | 2026-06-29 | 65% | A104, A106 | A104: FS, A106: FS
Phase 03 | A111 | Testing - Complete Car | Task Dependent | 2026-06-30 | 2026-07-31 | 0% | A107, A108, A109, A110 | A107: FS, A108: FS, A109: FS, A110:FS
Phase 04 | A112 | Test Reports and Validation | Task Dependent | 2026-08-01 | 2026-08-31 | 0% | A111 | A111: FS
Final | A116 | As-Build Drawings | Task Dependent | 2026-09-01 | 2026-09-29 | 0% | A112 | A112: FS
Final | A113 | Handover of Carbody | Finish Milestone |  | 2026-09-30 | 0% | A116 | A116: FS
Final | A114 | Final Carbody Report | Task Dependent | 2026-10-01 | 2026-10-25 | 0% | A113 | A113: FS
Final | A115 | Completion | Finish Milestone |  | 2026-10-25 | 0% | A114 | A114: FF
Formulas:
Start = [Finish, row above]+1
Finish = [Finish, row above]+1
Finish = [Start]+24