## Project Info
Project Name | Sample Project
Layout Name | Full View
Data Date | 2026-05-22

## Calendar
Setting | Value
Saturday Weekend | Yes
Sunday Weekend | Yes
2026 Public Holidays
2026-06-19
2026-07-02
2026-07-03
2026-07-25
2026-08-30
2027 Public Holidays
2027-01-01
2027-03-28
2027-12-31
2028 Public Holidays
2028-01-12
2028-06-15
2029 Public Holidays
2030 Public Holidays

## Activities
WBS | Activity ID | Activity Name | Task Type | Orig Duration (BD) | Start Date | Finish Date | % Complete | Predecessors
Engineering | AA | Start | Start Milestone | 0 | 2026-05-07 |  | 100
Engineering | AB | Task 01 | Task Dependent | 2 | 2026-05-08 | 2026-05-11 | 100 | AA-FS
Engineering | AC | Task 02 | Task Dependent | 3 | 2026-05-14 | 2026-05-18 | 100 | AB-FS+2
Engineering | AD | Task 03 | Task Dependent | 2 | 2026-05-21 | 2026-05-22 | 100 | AC-FF+4
Engineering | AE | Task 04 | Task Dependent | 3 | 2026-05-25 | 2026-05-27 |  | AD-FS, AC-FF+5
Engineering | AF | Task 05 | Task Dependent | 4 | 2026-05-28 | 2026-06-02 |  | AE-FF+4
Engineering | AG | Task 06 | Task Dependent | 5 | 2026-05-29 | 2026-06-04 |  | AF-SS+1
Engineering | AH | Task 07 | Task Dependent | 3 | 2026-06-05 | 2026-06-09 |  | AG-FS
Engineering | AI | Task 08 | Task Dependent | 4 | 2026-06-10 | 2026-06-15 |  | AH-FS
Engineering | AJ | Task 09 | Task Dependent | 2 | 2026-06-16 | 2026-06-17 |  | AI-FS
Engineering | AK | Task 10 | Task Dependent | 2 | 2026-06-18 | 2026-06-22 |  | AJ-FS
Engineering | AL | Task 11 | Task Dependent | 2 | 2026-06-23 | 2026-06-24 |  | AK-FS
Engineering | AM | Task 12 | Task Dependent | 2 | 2026-06-25 | 2026-06-26 |  | AL-FS
Procurement | AN | Task 13 | Task Dependent | 3 | 2026-06-29 | 2026-07-01 |  | AM-FS
Procurement | AO | Task 14 | Task Dependent | 4 | 2026-07-06 | 2026-07-09 |  | AN-FS
Procurement | AP | Task 15 | Task Dependent | 3 | 2026-07-10 | 2026-07-14 |  | AO-FS
Procurement | AQ | Task 16 | Task Dependent | 5 | 2026-07-15 | 2026-07-21 |  | AP-FS
Procurement | AR | Task 17 | Task Dependent | 4 | 2026-06-05 | 2026-06-10 |  | AG-FS
Procurement | AS | Task 18 | Task Dependent | 5 | 2026-07-22 | 2026-07-28 |  | AQ-FS
Procurement | AT | Task 19 | Task Dependent | 6 | 2026-07-29 | 2026-08-05 |  | AS-FS
Procurement | AU | Task 20 | Task Dependent | 7 | 2026-08-06 | 2026-08-14 |  | AT-FS
Procurement | AV | Task 21 | Task Dependent | 8 | 2026-06-11 | 2026-06-23 |  | AR-FS
Procurement | AW | Task 22 | Task Dependent | 4 | 2026-06-24 | 2026-06-29 |  | AV-FS
Construction | AX | Task 23 | Task Dependent | 2 | 2026-08-17 | 2026-08-18 |  | AW-FS, AU-FS
Construction | AY | Task 24 | Task Dependent | 2 | 2026-08-19 | 2026-08-20 |  | AX-FS
Construction | AZ | Task 25 | Task Dependent | 2 | 2026-08-21 | 2026-08-24 |  | AY-FS
Construction | BA | Task 26 | Task Dependent | 3 | 2026-08-25 | 2026-08-27 |  | AZ-FS
Construction | BB | Task 27 | Task Dependent | 5 | 2026-08-28 | 2026-09-03 |  | BA-FS
Construction | BC | Task 28 | Task Dependent | 5 | 2026-09-04 | 2026-09-10 |  | BB-FS
Construction | BD | Task 29 | Task Dependent | 1 | 2026-09-11 | 2026-09-11 |  | BC-FS, AD-FF+2
Construction | BE | Task 30 | Task Dependent | 3 | 2026-09-15 | 2026-09-17 |  | BD-FS+1
Construction | BF | Task 31 | Task Dependent | 2 | 2026-09-18 | 2026-09-21 |  | BE-FS
Construction | BG | Task 32 | Task Dependent | 4 | 2026-09-22 | 2026-09-25 |  | BF-FS
Construction | BH | Task 33 | Task Dependent | 5 | 2026-09-28 | 2026-10-02 |  | BG-FS
Construction | BI | Task34 | Task Dependent | 6 | 2026-10-05 | 2026-10-12 |  | BH-FS, AU-FS
Construction | BJ | Task 35 | Task Dependent | 7 | 2026-10-13 | 2026-10-21 |  | BI-FS
Construction | BK | Finish | Finish Milestone | 0 |  | 2026-10-21 |  | BJ-FF, AV-FS