## KMM Data
Data Date | Activity ID | Activity Name | Sched. Start | Sched. Finish | Actual Start | Actual Finish | Status | Task Type
2026-01-23 | A001 | Engineering Preliminary Design Complete |  | 2026-05-28 |  |  | Not Started | Finish Milestone
2026-02-24 | A001 | Engineering Preliminary Design Complete |  | 2026-05-22 |  |  | Not Started | Finish Milestone
2026-03-24 | A001 | Engineering Preliminary Design Complete |  | 2026-05-22 |  |  | Not Started | Finish Milestone
2026-04-24 | A001 | Engineering Preliminary Design Complete |  | 2026-05-22 |  |  | Not Started | Finish Milestone
2026-05-25 | A001 | Engineering Preliminary Design Complete |  | 2026-07-02 |  |  | Not Started | Finish Milestone
2026-01-23 | A002 | Engineering Detailed Design Complete |  | 2026-10-12 |  |  | Not Started | Finish Milestone
2026-02-24 | A002 | Engineering Detailed Design Complete |  | 2026-10-12 |  |  | Not Started | Finish Milestone
2026-03-24 | A002 | Engineering Detailed Design Complete |  | 2026-10-12 |  |  | Not Started | Finish Milestone
2026-04-24 | A002 | Engineering Detailed Design Complete |  | 2026-10-26 |  |  | Not Started | Finish Milestone
2026-05-25 | A002 | Engineering Detailed Design Complete |  | 2026-12-16 |  |  | Not Started | Finish Milestone
2026-01-23 | A003 | Engineering Final Design Complete |  | 2027-01-27 |  |  | Not Started | Finish Milestone
2026-02-24 | A003 | Engineering Final Design Complete |  | 2027-01-27 |  |  | Not Started | Finish Milestone
2026-03-24 | A003 | Engineering Final Design Complete |  | 2027-01-27 |  |  | Not Started | Finish Milestone
2026-04-24 | A003 | Engineering Final Design Complete |  | 2027-01-27 |  |  | Not Started | Finish Milestone
2026-05-25 | A003 | Engineering Final Design Complete |  | 2027-05-04 |  |  | Not Started | Finish Milestone
2026-01-23 | A004 | Procurement Stage 01 Complete |  | 2027-09-08 |  |  | Not Started | Finish Milestone
2026-02-24 | A004 | Procurement Stage 01 Complete |  | 2027-09-08 |  |  | Not Started | Finish Milestone
2026-03-24 | A004 | Procurement Stage 01 Complete |  | 2027-09-08 |  |  | Not Started | Finish Milestone
2026-04-24 | A004 | Procurement Stage 01 Complete |  | 2027-09-08 |  |  | Not Started | Finish Milestone
2026-05-25 | A004 | Procurement Stage 01 Complete |  | 2027-12-09 |  |  | Not Started | Finish Milestone
2026-01-23 | A005 | Procurement Stage 02 Complete |  | 2026-05-29 |  |  | Not Started | Finish Milestone
2026-02-24 | A005 | Procurement Stage 02 Complete |  | 2026-05-29 |  |  | Not Started | Finish Milestone
2026-03-24 | A005 | Procurement Stage 02 Complete |  | 2026-05-29 |  |  | Not Started | Finish Milestone
2026-04-24 | A005 | Procurement Stage 02 Complete |  | 2026-05-29 |  |  | Not Started | Finish Milestone
2026-05-25 | A005 | Procurement Stage 02 Complete |  | 2026-05-29 |  |  | Not Started | Finish Milestone
2026-01-23 | A006 | Overall Building 01 Construction |  | 2026-05-18 | 2025-07-07 |  | In Progress | Task
2026-02-24 | A006 | Overall Building 01 Construction |  | 2026-05-18 | 2025-07-07 |  | In Progress | Task
2026-03-24 | A006 | Overall Building 01 Construction |  | 2026-05-18 | 2025-07-07 |  | In Progress | Task
2026-04-24 | A006 | Overall Building 01 Construction |  | 2026-05-12 | 2025-07-07 |  | In Progress | Task
2026-05-25 | A006 | Overall Building 01 Construction |  |  | 2025-07-07 | 2026-05-21 | Completed | Task
2026-01-23 | A007 | Overall Building 02 Construction |  | 2026-05-27 | 2026-01-15 |  | In Progress | Task
2026-02-24 | A007 | Overall Building 02 Construction |  | 2026-05-27 | 2026-01-15 |  | In Progress | Task
2026-03-24 | A007 | Overall Building 02 Construction |  | 2026-05-27 | 2026-01-15 |  | In Progress | Task
2026-04-24 | A007 | Overall Building 02 Construction |  | 2026-05-26 | 2026-01-15 |  | In Progress | Task
2026-05-25 | A007 | Overall Building 02 Construction |  | 2026-05-26 | 2026-01-15 |  | In Progress | Task
2026-01-23 | A008 | Overall Building 03 Construction | 2026-05-30 | 2026-09-30 |  |  | Not Started | Task
2026-02-24 | A008 | Overall Building 03 Construction | 2026-05-30 | 2026-09-30 |  |  | Not Started | Task
2026-03-24 | A008 | Overall Building 03 Construction | 2026-05-30 | 2026-09-30 |  |  | Not Started | Task
2026-04-24 | A008 | Overall Building 03 Construction |  | 2026-09-23 | 2026-05-28 |  | In Progress | Task
2026-05-25 | A008 | Overall Building 03 Construction |  | 2026-09-23 | 2026-05-28 |  | In Progress | Task
2026-01-23 | A009 | Contruction Completed |  | 2026-10-16 |  |  | Not Started | Finish Milestone
2026-02-24 | A009 | Contruction Completed |  | 2026-10-16 |  |  | Not Started | Finish Milestone
2026-03-24 | A009 | Contruction Completed |  | 2026-10-16 |  |  | Not Started | Finish Milestone
2026-04-24 | A009 | Contruction Completed |  | 2026-11-23 |  |  | Not Started | Finish Milestone
2026-05-25 | A009 | Contruction Completed |  | 2026-11-23 |  |  | Not Started | Finish Milestone
2026-01-23 | A010 | Commissioning Commence | 2026-12-23 |  |  |  | Not Started | Start Milestone
2026-02-24 | A010 | Commissioning Commence | 2026-12-22 |  |  |  | Not Started | Start Milestone
2026-03-24 | A010 | Commissioning Commence | 2026-12-22 |  |  |  | Not Started | Start Milestone
2026-04-24 | A010 | Commissioning Commence | 2027-01-29 |  |  |  | Not Started | Start Milestone
2026-05-25 | A010 | Commissioning Commence | 2027-04-07 |  |  |  | Not Started | Start Milestone
2026-01-23 | A011 | Commissioning Building 01 Overall |  | 2026-06-24 | 2025-09-15 |  | In Progress | Task
2026-02-24 | A011 | Commissioning Building 01 Overall |  | 2026-06-24 | 2025-09-15 |  | In Progress | Task
2026-03-24 | A011 | Commissioning Building 01 Overall |  | 2026-06-24 | 2025-09-15 |  | In Progress | Task
2026-04-24 | A011 | Commissioning Building 01 Overall |  | 2026-06-24 | 2025-09-15 |  | In Progress | Task
2026-05-25 | A011 | Commissioning Building 01 Overall |  | 2026-07-06 | 2025-09-15 |  | In Progress | Task
2026-01-23 | A012 | Commissioning Building 02 Overall | 2026-03-10 | 2026-07-02 |  |  | Not Started | Task
2026-02-24 | A012 | Commissioning Building 02 Overall | 2026-03-05 | 2026-07-02 |  |  | Not Started | Task
2026-03-24 | A012 | Commissioning Building 02 Overall | 2026-03-25 | 2026-07-02 |  |  | Not Started | Task
2026-04-24 | A012 | Commissioning Building 02 Overall |  | 2026-07-02 | 2026-03-30 |  | In Progress | Task
2026-05-25 | A012 | Commissioning Building 02 Overall |  | 2026-07-13 | 2026-03-30 |  | In Progress | Task
2026-01-23 | A013 | Commissioning Building 03 Overall | 2026-10-01 | 2026-12-08 |  |  | Not Started | Task
2026-02-24 | A013 | Commissioning Building 03 Overall | 2026-10-01 | 2026-12-08 |  |  | Not Started | Task
2026-03-24 | A013 | Commissioning Building 03 Overall | 2026-10-01 | 2026-12-08 |  |  | Not Started | Task
2026-04-24 | A013 | Commissioning Building 03 Overall | 2026-09-11 | 2026-11-21 |  |  | Not Started | Task
2026-05-25 | A013 | Commissioning Building 03 Overall | 2026-09-23 | 2026-12-03 |  |  | Not Started | Task
2026-01-23 | A014 | Overall Commissioning Complete |  | 2026-12-18 |  |  | Not Started | Finish Milestone
2026-02-24 | A014 | Overall Commissioning Complete |  | 2026-12-18 |  |  | Not Started | Finish Milestone
2026-03-24 | A014 | Overall Commissioning Complete |  | 2026-12-30 |  |  | Not Started | Finish Milestone
2026-04-24 | A014 | Overall Commissioning Complete |  | 2026-12-14 |  |  | Not Started | Finish Milestone
2026-05-25 | A014 | Overall Commissioning Complete |  | 2026-12-24 |  |  | Not Started | Finish Milestone
2026-01-23 | A015 | Commencement of Common Area Utility Works | 2027-03-05 |  |  |  | Not Started | Start Milestone
2026-02-24 | A015 | Commencement of Common Area Utility Works | 2027-03-05 |  |  |  | Not Started | Start Milestone
2026-03-24 | A015 | Commencement of Common Area Utility Works | 2027-03-02 |  |  |  | Not Started | Start Milestone
2026-04-24 | A015 | Commencement of Common Area Utility Works | 2027-02-12 |  |  |  | Not Started | Start Milestone
2026-05-25 | A015 | Commencement of Common Area Utility Works | 2027-02-24 |  |  |  | Not Started | Start Milestone
2026-01-23 | A016 | Ccompletion of Common Area Underground Works |  | 2026-03-20 |  |  | Not Started | Finish Milestone
2026-02-24 | A016 | Ccompletion of Common Area Underground Works |  | 2026-03-20 |  |  | Not Started | Finish Milestone
2026-03-24 | A016 | Ccompletion of Common Area Underground Works |  | 2026-03-25 |  |  | Not Started | Finish Milestone
2026-04-24 | A016 | Ccompletion of Common Area Underground Works |  | 2026-04-28 |  |  | Not Started | Finish Milestone
2026-05-25 | A016 | Ccompletion of Common Area Underground Works |  | 2026-11-27 |  |  | Not Started | Finish Milestone
2026-01-23 | A017 | Installation of Pump Station | 2026-02-27 | 2026-10-08 |  |  | Not Started | Task
2026-02-24 | A017 | Installation of Pump Station | 2026-02-27 | 2026-10-08 |  |  | Not Started | Task
2026-03-24 | A017 | Installation of Pump Station | 2026-04-02 | 2026-11-17 |  |  | Not Started | Task
2026-04-24 | A017 | Installation of Pump Station | 2026-05-19 | 2026-12-02 |  |  | Not Started | Task
2026-05-25 | A017 | Installation of Pump Station | 2026-11-30 | 2027-06-24 |  |  | Not Started | Task
2026-01-23 | A018 | Installation of Generator | 2026-03-24 | 2026-09-22 |  |  | Not Started | Task
2026-02-24 | A018 | Installation of Generator | 2026-04-10 | 2026-10-08 |  |  | Not Started | Task
2026-03-24 | A018 | Installation of Generator | 2026-05-11 | 2026-11-06 |  |  | Not Started | Task
2026-04-24 | A018 | Installation of Generator | 2026-05-19 | 2026-11-17 |  |  | Not Started | Task
2026-05-25 | A018 | Installation of Generator | 2026-11-30 | 2027-06-08 |  |  | Not Started | Task
2026-01-23 | A019 | Construction of Power Station | 2026-03-24 | 2026-09-03 |  |  | Not Started | Task
2026-02-24 | A019 | Construction of Power Station | 2026-03-24 | 2026-09-03 |  |  | Not Started | Task
2026-03-24 | A019 | Construction of Power Station | 2026-05-01 | 2026-10-13 |  |  | Not Started | Task
2026-04-24 | A019 | Construction of Power Station | 2026-05-19 | 2026-10-29 |  |  | Not Started | Task
2026-05-25 | A019 | Construction of Power Station | 2026-11-30 | 2027-05-20 |  |  | Not Started | Task
2026-01-23 | A020 | Commencement of Gridline Installation | 2027-06-21 |  |  |  | Not Started | Start Milestone
2026-02-24 | A020 | Commencement of Gridline Installation | 2027-06-21 |  |  |  | Not Started | Start Milestone
2026-03-24 | A020 | Commencement of Gridline Installation | 2027-07-29 |  |  |  | Not Started | Start Milestone
2026-04-24 | A020 | Commencement of Gridline Installation | 2027-08-16 |  |  |  | Not Started | Start Milestone
2026-05-25 | A020 | Commencement of Gridline Installation | 2028-03-02 |  |  |  | Not Started | Start Milestone
2026-01-23 | A021 | Completion of Underground Works around Power Station |  | 2027-09-06 |  |  | Not Started | Finish Milestone
2026-02-24 | A021 | Completion of Underground Works around Power Station |  | 2027-09-02 |  |  | Not Started | Finish Milestone
2026-03-24 | A021 | Completion of Underground Works around Power Station |  | 2027-09-28 |  |  | Not Started | Finish Milestone
2026-04-24 | A021 | Completion of Underground Works around Power Station |  | 2027-10-14 |  |  | Not Started | Finish Milestone
2026-05-25 | A021 | Completion of Underground Works around Power Station |  | 2028-05-05 |  |  | Not Started | Finish Milestone
2026-01-23 | A022 | Completion of Power Station |  | 2028-07-22 |  |  | Not Started | Finish Milestone
2026-02-24 | A022 | Completion of Power Station |  | 2028-07-22 |  |  | Not Started | Finish Milestone
2026-03-24 | A022 | Completion of Power Station |  | 2028-03-29 |  |  | Not Started | Finish Milestone
2026-04-24 | A022 | Completion of Power Station |  | 2028-04-14 |  |  | Not Started | Finish Milestone
2026-05-25 | A022 | Completion of Power Station |  | 2028-11-04 |  |  | Not Started | Finish Milestone
2026-01-23 | A023 | Commencement of Handingover | 2032-07-21 |  |  |  | Not Started | Start Milestone
2026-02-24 | A023 | Commencement of Handingover | 2032-07-21 |  |  |  | Not Started | Start Milestone
2026-03-24 | A023 | Commencement of Handingover | 2032-08-30 |  |  |  | Not Started | Start Milestone
2026-04-24 | A023 | Commencement of Handingover | 2032-09-15 |  |  |  | Not Started | Start Milestone
2026-05-25 | A023 | Commencement of Handingover | 2033-03-31 |  |  |  | Not Started | Start Milestone
2026-01-23 | A024 | Completion of Handingover |  | 2032-08-10 |  |  | Not Started | Finish Milestone
2026-02-24 | A024 | Completion of Handingover |  | 2032-08-10 |  |  | Not Started | Finish Milestone
2026-03-24 | A024 | Completion of Handingover |  | 2032-09-16 |  |  | Not Started | Finish Milestone
2026-04-24 | A024 | Completion of Handingover |  | 2032-10-06 |  |  | Not Started | Finish Milestone
2026-05-25 | A024 | Completion of Handingover |  | 2033-04-21 |  |  | Not Started | Finish Milestone
2026-01-23 | A025 | Project Completion |  | 2033-02-09 |  |  | Not Started | Finish Milestone
2026-02-24 | A025 | Project Completion |  | 2033-02-09 |  |  | Not Started | Finish Milestone
2026-03-24 | A025 | Project Completion |  | 2033-03-18 |  |  | Not Started | Finish Milestone
2026-04-24 | A025 | Project Completion |  | 2033-04-07 |  |  | Not Started | Finish Milestone
2026-05-25 | A025 | Project Completion |  | 2033-10-21 |  |  | Not Started | Finish Milestone

## Sheet1
Activity ID | Activity Name | OD | Start | Finish | Total Float
QTMP - ROLLINGSTOCK WORKS PROGRAM - JAN26 |  | 1924 | 07-Jul-25 A | 1933-02-09 | 0
PROJECT MILESTONES |  | 1417 | 2027-09-06 | 1933-02-09 | 0
New Schedule A2 milestone (FSAD) |  | 1417 | 2027-09-06 | 1933-02-09 | 0
Part 3 Multiple Unit Delivery (Initial Fleet) |  | 1417 | 2027-09-06 | 1933-02-09 | 0
MUs Date for Commencement of Mainline Dynamic Testing |  | 0 | 1932-07-21 | 1932-07-21 | 13
MUs Date for Provisional Acceptance |  | 1222 | 2027-09-06 | 1932-08-10 | 122
MUs Date for Final Acceptance |  | 1663 | 2028-07-22 | 1933-02-09 | 0
MANUFACTURING |  | 313 | 07-Jul-25 A | 2026-12-08 | 117
TTP01 |  | 294 | 07-Jul-25 A | 2026-09-30 | 114
SUMMARY TTP01 |  | 294 | 07-Jul-25 A | 2026-09-30 | 114
TTP02 |  | 323 | 15-Sep-25 A | 2026-12-08 | 130
SUMMARY TTP02 |  | 323 | 15-Sep-25 A | 2026-12-08 | 130
LOE-21 | TTP02 - Single Car Test | 94 | 2026-03-10 | 2026-07-02 | 192
MU01 |  | 143 | 2026-02-27 | 2026-10-08 | 1
SUMMARY MU01 |  | 143 | 2026-02-27 | 2026-10-08 | 1
QTMP - ROLLINGSTOCK WORKS PROGRAM - FEB26 |  | 1924 | 07-Jul-25 A | 1933-02-09 | 0
PROJECT MILESTONES |  | 1419 | 2027-09-02 | 1933-02-09 | 0
New Schedule A2 milestone (FSAD) |  | 1419 | 2027-09-02 | 1933-02-09 | 0
Part 3 Multiple Unit Delivery (Initial Fleet) |  | 1419 | 2027-09-02 | 1933-02-09 | 0
MUs Date for Commencement of Mainline Dynamic Testing |  | 0 | 1932-07-21 | 1932-07-21 | 13
MUs Date for Provisional Acceptance |  | 1224 | 2027-09-02 | 1932-08-10 | 122
MUs Date for Final Acceptance |  | 1663 | 2028-07-22 | 1933-02-09 | 0
MANUFACTURING |  | 313 | 07-Jul-25 A | 2026-12-08 | 117
TTP01 |  | 294 | 07-Jul-25 A | 2026-09-30 | 115
SUMMARY TTP01 |  | 294 | 07-Jul-25 A | 2026-09-30 | 115
TTP02 |  | 323 | 15-Sep-25 A | 2026-12-08 | 130
SUMMARY TTP02 |  | 323 | 15-Sep-25 A | 2026-12-08 | 130
LOE-21 | TTP02 - Single Car Test | 98 | 2026-03-05 | 2026-07-02 | 192
MU01 |  | 143 | 2026-02-27 | 2026-10-08 | 1
SUMMARY MU01 |  | 143 | 2026-02-27 | 2026-10-08 | 1
QTMP - ROLLINGSTOCK WORKS PROGRAM - MAR26 |  | 1951 | 07-Jul-25 A | 1933-03-18 | 121
PROJECT MILESTONES |  | 1428 | 2027-09-28 | 1933-03-18 | 121
New Schedule A2 milestone (FSAD) |  | 1428 | 2027-09-28 | 1933-03-18 | 121
Part 3 Multiple Unit Delivery (Initial Fleet) |  | 1428 | 2027-09-28 | 1933-03-18 | 121
MUs Date for Commencement of Mainline Dynamic Testing |  | 0 | 1932-08-30 | 1932-08-30 | 13
MUs Date for Provisional Acceptance |  | 1232 | 2027-09-28 | 1932-09-16 | 239
MUs Date for Final Acceptance |  | 1815 | 2028-03-29 | 1933-03-18 | 171
MANUFACTURING |  | 313 | 07-Jul-25 A | 2026-12-08 | 909
TTP01 |  | 294 | 07-Jul-25 A | 2026-09-30 | 1059
SUMMARY TTP01 |  | 294 | 07-Jul-25 A | 2026-09-30 | 1059
TTP02 |  | 323 | 15-Sep-25 A | 2026-12-08 | 1065
SUMMARY TTP02 |  | 323 | 15-Sep-25 A | 2026-12-08 | 1065
LOE-21 | TTP02 - Single Car Test | 81 | 2026-03-25 | 2026-07-02 | 1126
MU01 |  | 146 | 2026-04-02 | 2026-11-17 | 1
SUMMARY MU01 |  | 146 | 2026-04-02 | 2026-11-17 | 1
QTMP - ROLLINGSTOCK WORKS PROGRAM - APR26 |  | 1965 | 07-Jul-25 A | 1933-04-07 | 107
PROJECT MILESTONES |  | 1430 | 2027-10-14 | 1933-04-07 | 107
New Schedule A2 milestone (FSAD) |  | 1430 | 2027-10-14 | 1933-04-07 | 107
Part 3 Multiple Unit Delivery (Initial Fleet) |  | 1430 | 2027-10-14 | 1933-04-07 | 107
MUs Date for Commencement of Mainline Dynamic Testing |  | 0 | 1932-09-15 | 1932-09-15 | 14
MUs Date for Provisional Acceptance |  | 1234 | 2027-10-14 | 1932-10-06 | 226
MUs Date for Final Acceptance |  | 1819 | 2028-04-14 | 1933-04-07 | 151
MANUFACTURING |  | 309 | 07-Jul-25 A | 2026-12-02 | 922
TTP01 |  | 291 | 07-Jul-25 A | 2026-09-23 | 1116
SUMMARY TTP01 |  | 291 | 07-Jul-25 A | 2026-09-23 | 1116
TTP02 |  | 309 | 15-Sep-25 A | 2026-11-21 | 1090
SUMMARY TTP02 |  | 309 | 15-Sep-25 A | 2026-11-21 | 1090
LOE-21 | TTP02 - Single Car Test | 54 | 30-Mar-26 A | 2026-07-02 | 1136
MU01 |  | 128 | 2026-05-19 | 2026-12-02 | 1
SUMMARY MU01 |  | 128 | 2026-05-19 | 2026-12-02 | 1
QTMP - ROLLINGSTOCK WORKS PROGRAM - MAY26 |  | 2106 | 07-Jul-25 A | 1933-10-21 | 0
PROJECT MILESTONES |  | 1425 | 2028-05-05 | 1933-10-21 | 0
New Schedule A2 milestone (FSAD) |  | 1425 | 2028-05-05 | 1933-10-21 | 0
Part 3 Multiple Unit Delivery (Initial Fleet) |  | 1425 | 2028-05-05 | 1933-10-21 | 0
MUs Date for Commencement of Mainline Dynamic Testing |  | 0 | 1933-03-31 | 1933-03-31 | 16
MUs Date for Provisional Acceptance |  | 1231 | 2028-05-05 | 1933-04-21 | 127
MUs Date for Final Acceptance |  | 1812 | 2028-11-04 | 1933-10-21 | 0
MANUFACTURING |  | 455 | 07-Jul-25 A | 2027-06-24 | 922
TTP01 |  | 291 | 07-Jul-25 A | 2026-09-23 | 1249
SUMMARY TTP01 |  | 291 | 07-Jul-25 A | 2026-09-23 | 1249
TTP02 |  | 319 | 15-Sep-25 A | 2026-12-03 | 1255
SUMMARY TTP02 |  | 319 | 15-Sep-25 A | 2026-12-03 | 1255
LOE-21 | TTP02 - Single Car Test | 54 | 30-Mar-26 A | 2026-07-13 | 1303
MU01 |  | 128 | 2026-11-30 | 2027-06-24 | 1
SUMMARY MU01 |  | 128 | 2026-11-30 | 2027-06-24 | 1