## Task-Resource Mapping
Task ID | Task Name | Project | Discipline | Location | Planned Start | Planned End | Actual Start | Actual End | Status | Project Title | Default Hrs/Day | Role | Assigned Resource ID | Assigned Resource Name | Role Start | Role End | Role Hrs/Day
TASK-001 | Substructure Works - Area 01 | ZFA | Plumbing and Electrical | ZFA - Area 01 | 2026-08-07 | 2026-08-28 |  |  | Not Started | ZFA | 8 | Plumber | RES-003 | Karen | 2026-08-07 | 2026-08-28 | 8
TASK-001 | Substructure Works - Area 01 | ZFA | Plumbing and Electrical | ZFA - Area 01 | 2026-08-07 | 2026-08-28 |  |  | Not Started | ZFA | 8 | Electrician | RES-002 | Diego Thiago | 2026-08-10 | 2026-08-14 | 8
TASK-002 | Concrete - Area 02 | ZFA | Civil | ZFA - Area 02 | 2026-06-02 | 2026-06-19 |  |  | Not Started | ZFA | 8 | General Mason | RES-001 | Andrew Tait | 2026-06-02 | 2026-06-19 | 8
TASK-002 | Concrete - Area 02 | ZFA | Civil | ZFA - Area 02 | 2026-06-02 | 2026-06-19 |  |  | Not Started | ZFA | 8 | Plumber | RES-004 | Matthew | 2026-06-02 | 2026-06-19 | 8

## Public Holidays
Date | Holiday Name
2026-08-11 | dummy
2026-08-12 | dummy
2026-08-14 | dummy